## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
all | Implement base project | 0.5 | 0 | 0 | 0 | 0
view receipt entries | Implement UI for Receipt List window | 2 | 2 | 2 | 2 | 0
| Implement Receipt and ReceiptBook classes | 1 | 1 | 1 | 1 | 0
add receipt entry | Implement UI for Receipt Details window | 2 | 2 | 2 | 2 | 0
| Implement behavior of Add and Save buttons | 1 | 1 | 1 | 1 | 0
| Implement addReceipt method in ReceiptBook class | 0.5 | 0.5 | 0.5 | 0.5 | 0
edit receipt details | Implement behavior of Edit button to load the selected receipt | 1 | 1 | 1 | 1 | 0
| Implement update methods with precondition checks in Receipt class | 1 | 1 | 1 | 1 | 0
assign category | Implement Category enum | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Implement category selection in Receipt Details window | 0.5 | 0.5 | 0.5 | 0.5 | 0
mark tax-related | Implement tax-related flag in Receipt class | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Implement tax-related checkbox in Receipt Details window | 0.5 | 0.5 | 0.5 | 0.5 | 0
delete receipt entry | Implement removeReceipt method in ReceiptBook class | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Implement behavior of Delete button | 0.5 | 0.5 | 0.5 | 0.5 | 0
view total per category | Implement UI for Spending Summary window | 2 | 2 | 2 | 2 | 0
| Implement totalForCategory method in ReceiptSummary class | 1 | 1 | 1 | 1 | 0
view total within date range | Implement totalBetween method in ReceiptSummary class | 1 | 1 | 1 | 1 | 0
| Implement date range selection in Spending Summary window | 1 | 1 | 1 | 1 | 0
view tax-related total | Implement totalTaxRelated method in ReceiptSummary class | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Implement display of tax-related total in Spending Summary window | 0.5 | 0.5 | 0.5 | 0.5 | 0
search by vendor | Implement searchByVendor method in ReceiptBook class | 1 | 1 | 1 | 1 | 0
| Write tests for searchByVendor in ReceiptBook class | 1 | 1 | 1 | 1 | 0
| Implement search field in Receipt List window | 1 | 1 | 1 | 1 | 0
| Implement behavior of Search and Clear buttons | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Estimate Totals | 21.5 | 21 | 21 | 21 | 0